## Manpower Efforts
Sr.No. | Work Type | Work details | Volume Calculation Details | Resource Type | Work Volume | Efforts Per Unit | Hours Needed
1 | Project Management
|  | Kick off PPT |  | Project Manager | 1 | 4 | 4
|  | * Fortnightly Status Report | 6 months | Project Manager | 12 | 2 | 24
|  | Project Activities Coordination |  | Business Analyst | 1 | 80 | 80
2 | Wireframe, IA & Content Management
|  | Wireframe |  | Designer | 12 | 8 | 96
|  | Information Architecture (IA) |  | Designer | 1 | 4 | 4
|  | Content Collection & Integration | 300 pages | Content Operator | 300 | 0.5 | 150
|  | SRS Document Creation |  | Business Analyst | 1 | 80 | 80
3 | Graphics & UI Work
|  | Design Theme Creation & Finalization |  | Designer | 2 | 40 | 80
|  | HTML Conversion & Integration in CMS |  | Designer | 2 | 60 | 120
|  | Graphics Work |  | Designer | 4 | 4 | 16
4 | Configuration & Customisation of Pre-built CMS System
|  | Live code Setup & Configuration of CMS | Folder creation, DB creation, Module Activation/Deactivation, FTP setup | System Admin | 1 | 40 | 40
|  | Design Theme Integration |  | Developer | 2 | 24 | 48
|  | Production Server Source Code Download |  | Developer | 1 | 8 | 8
5 | *New Modules Development & Integration (if any)
|  | User Management |  | Developer | 1 | 30 | 30
|  | Role Management |  | Developer | 1 | 40 | 40
|  | Workflow Management |  | Developer | 1 | 39 | 39
|  | Alerts & Notification |  | Developer | 3 | 16 | 16
|  | Contact Us Module |  | Developer | 5 | 16 | 16
|  | Invoice Management |  | Sr.developer | 12 | 16 | 192
|  | Centralized query redressal & monitoring system |  | Sr.developer | 5 | 16 | 80
|  | MIS Reports |  | Developer | 8 | 16 | 128
|  | Dashboard Management Module |  | Developer | 5 | 24 | 120
|  | Latest Events |  | Developer | 1 | 16 | 16
|  | Latest News |  | Developer | 1 | 16 | 16
|  | Revenue Management System |  | Sr.developer | 8 | 32 | 256
|  | Archive Management |  | Sr.developer | 4 | 24 | 96
|  | Migration of Existing Website |  | Developer | 1 | 120 | 120
|  | API Integration |  | Sr.developer | 5 | 24 | 120
Integration Components
|  | Google Search API integration |  | Developer | 1 | 8 | 8
|  | SMTP configuration |  | Developer | 1 | 8 | 8
|  | SMS and Email Integration |  | Developer | 1 | 20 | 20
|  | Payment Gateway |  | Developer | 1 | 40 | 40
6 | QC & UAT
|  | Internal |  |  | 2 | 40 | 80
|  | Customer |  |  | 2 | 40 | 80
7 | SSL Certificate |  |  | System Admin | 1 | 3 | 3
8 | Cert-in Security Audit | L1 & L2 Report fixing |  | Developer | 2 | 60 | 120
|  | Fixing prodcution Server Vulnerability |  | System Admin | 2 | 40 | 80
| VAPT | L1 & L2 Report fixing |  | System Admin | 1 | 80 | 80
9 | Deployment to Production Server |  | VPN details follow up, Server details follow up, VA Score fixing/ follow up | Project Manager | 1 | 16 | 16
10 | User Manual & Training
|  | User Manual |  |  | 2 | 8 | 16
|  | Training |  |  | 2 | 8 | 16
11 | STQC
|  | Web Quality Manual Customization & Approval |  | Project Manager | 1 | 8 | 8
|  | STQC Coordination | Project Manager Activity | Project Manager | 1 | 20 | 20
|  | Bug Fixing & Closure GIGW 3.0 |  | Developer | 1 | 110 | 110
12 | Hand Over
|  | Source Code handover to dept. |  | Project Manager | 1 | 4 | 4
|  | Support Team Email |  | Project Manager | 1 | 1 | 1
|  |  | Total hour. |  |  |  | 2520
|  |  | Total days |  |  |  | 315
* Depend on RFP