## Slide 1: DESIGN, DEVELOPMENT, HOSTING AND MAINTENANCE OF PRAAPTI WEB PORTAL and MOBILE APPLICATION Project Kick-Off Meeting
Meeting Date | 01-September-2025
Presented By | Nikhil Singh

## Slide 2: Meeting Agenda
About NCM
Project Objectives
Understanding of Project Scope
Project Phase-wise Scope
Software Environment
Web Portal Development Flow
Journey Till Milestone
Approach for going forward
Project Development Plan
Deliverables
Appropriate Delegation and Accountability of stakeholders
Expected Challenges faced
Mythology We Used
Management Team Details

## Slide 3
About NetCreativeMind
National Awards
CMMI Level 3
Founded in 2002, wholly owned by NetCreativeMind Solutions Pvt Ltd
23+ Years’
Experience
Certifications
1000+
Projects Completed
250+
Govt. Projects
25+
25+ Countries Served
Achievements
Web Ratna Award
Project Completed
ISO 9001 – 2015 Certificate
ISO 27000:2018 Certificate
NetCreativeMind Solutions is prominent Information and Communication Technology (ICT) Services Provider and Solutions Company that provides the services such as E-Governance solutions, Software Accessibility, Staffing Solutions, Outsourcing Development, and OEM's Partner Products in India and abroad. It covers the Government and Public Sector at a massive scale and its software makes the organization work easy to handle.

## Slide 4: Project Objectives
To modernize and enhance the PRAAPTI Web Portal and Mobile Application, aligning with industry best practices to ensure transparency, accountability, and efficiency in the power procurement process under the Ministry of Power, Government of India.
Core Focus Areas
Real-time monitoring & central auditing
Seamless stakeholder engagement
Robust data protection & compliance with LPS Rules, 2022
Modernized, user-friendly, and bilingual design
Scalable hosting with disaster recovery and backups

## Slide 5: Key Objectives
Transparency & Compliance
  Ensure invoicing & payments as per LPS Rules, 2022
  Centralized invoice and payment management
User Experience
  Intuitive, bilingual, responsive design
  Accessibility for differently-abled users
Process Efficiency
  Entity registration, invoice management, bulk uploads
  Automated notifications & query redressal
Data Security & Standards
  SSL encryption, role-based access, API security
  Virtual firewalls & disaster recovery
  STQC certification compliance
Decision Support
  Dashboards for graphical data & MIS reporting
  Customized reports for stakeholders
Infrastructure
  Migration to MeitY-empanelled GCC
  Dedicated environments (development, testing, production)
  Domain mapping, backups & disaster recovery

## Slide 6: Understanding of Project Scope
Functional
Web Portal & Mobile App Development
User Management
UI/UX Enhancements
Billing & Revenue Management
Centralized Query Redressal & Monitoring
MIS Reporting & Dashboards
Security & Data Protection
Database Management
API Integration (to be provided by client)
Archive Management
In-site Search Module
Admin & Content Management
Non-Functional
SSL Implementation
STQC Certification
Disaster Recovery Setup
Bilingual Support
Accessibility for Differently-abled Users
Hosting & Migration
Migration to MeitY-empanelled GCC
Domain mapping & application hosting
Backup & restore mechanisms
Security arrangements in place
Disaster recovery tested & documented
Regular environment reviews & performance reports
Maintenance & Operations : 3-year AMC with 2 manpower deployment

## Slide 7: Project Phase-Wise Scope (Aligned with Milestones)
Milestone 1: Requirement Gathering & SRS
  Stakeholder consultations
  Requirement analysis & documentation
  Submission & approval of Software Requirement Specification (SRS)
Milestone 3: Infrastructure & Migration
  Allocation of cloud infrastructure (MeitY-empanelled GCC)
  Database migration from existing server
  SSL implementation & security arrangements
  Functionality verification of migrated portal & app
Milestone 2: Development & Testing
  Web Portal & Mobile App development
  UI/UX enhancements
  Module implementation: User Management, Billing, Query Redressal, Reports
  Functional & security testing
  CERT-IN security audit
Milestone 4: Training & Go-Live Support
  User training sessions for stakeholders
  Handover of technical & functional documents
  Successful live operations for 3 months (stabilization phase)
Milestone 5: Maintenance & Enhancements
  3-year Operation & Maintenance support with manpower deployment
  Ongoing maintenance, performance monitoring & bug fixes
  Feature updates & enhancements as per stakeholder needs

## Slide 8: Software Environment
  Operating System : UBUNTU
  Mobile Application : React Native
  Database : My SQL
  Language : PHP Framework Laravel

## Slide 9: Web Portal Development Flow

## Slide 10: Journey till Milestone 1 : 2 Weeks : Finalization of SRS
STAGE 01
STAGE 03
STAGE 02
STAGE 04
Requirement Gathering
SRS Preparation
SRS Review
Milestone 1 Signoff

## Slide 11: Journey till Milestone 2 : 20 Weeks: Development & Testing
STAGE 01
STAGE 03
STAGE 02
STAGE 04
STAGE 05
Web Portal & Mobile Application development completed
Functional & security testing conducted
Web Portal Wireframe Design
CERT-IN security audit done
Milestone 2 Signoff

## Slide 12: Journey Till Milestone 3 : 7 weeks : Infrastructure & Migration
STAGE 01
STAGE 03
STAGE 02
STAGE 04
STAGE 05
STAGE 06
PRAAPTI Portal migrated to MeitY-empanelled GCC
Database migration from old server completed
SSL certificate implemented & verified
Security arrangements tested
Demonstration
UAT Approval by Department
Milestone 3 Signoff

## Slide 13: Journey till Milestone 4 (Training & Go-Live Suppor)
STAGE 01
STAGE 03
STAGE 02
STAGE 04
User training initiated
Handover documents being prepared
3-month live monitoring phase started
Milestone 4 Signoff

## Slide 14: Approach for Going Forward
Web portal’s wireframe & SRS finalisation and approval by the department.
NetCreativeMind (NCM) team to create web portal design template, Wireframe and document the Software Requirement Specification (SRS) in discussion with department. Department to review and approve web Portal UI design, Wireframe and SRS.
Content compilation for each link of approved design and delivery of final content (English & Hindi ) by department as per plan.
Completion of Milestone-2, functionality development & testing by NCM team based on approved design, wireframe and SRS document.
Department to apply for NIC/GOV domain name and NIC staging/production servers, FTP & VPN, email services with SMTPS .
Milestone-3 [UAT & migration] to be performed & approved by department.
After UAT approval, Web portal will be hosted on staging server and submitted to external auditing company for security audit by NCM team. On completion of security audit, Safe to Host certificate & audit report will be issued.

## Slide 15: Project Development Plan

## Slide 16: Deliverables
1.SRS Document
2.Detailed Project Plan, Functional Specifications and Design documents.
3.Ownership of all source code
4.Data Migration Document
5.Technical Manuals, User Manuals and Training material
6.CERT-IN Empaneled STQC audit &Functional Audit Report
7.Data Backup / Archival process
8.FAQ and web Portal & Mobile Application policy
9. Security Audit
10. SSL certificate
11. Strictly comply to all national and international copyright, IPR and trademark requirements
for all content available
12.Non-disclosure agreement
13.Training & Support
14. Disaster Recovery

## Slide 17
Appropriate Delegation and
Accountability of stakeholders
Activities | NCM | Department
Nodal officer(SPOC) for Smooth Project Execution |  | 
Preparation of all the documents like Wireframe SRS, User Manual etc. |  | 
Approval on time of the all the documents like Wireframe, SRS, User Manual etc. |  | 
Development of Web Portal |  | 
Facility, credentials and API for integration with 3rd party service |  | 
Back Up |  | 
Email Service provisioning |  | 
Signoff UAT & Go-Live of the Web Portal |  | 
All Infra (Hardware & Software) required for hosting the application |  | 
Configuration of Application |  | 
Configuration of Database server |  | 
Application & DB Server Configuration (pre-requisites) |  | 
Network Configuration |  | 
Security & Backup |  | 
Monitoring & Server Maintenance |  | 
Facility and credentials for Data Migration |  | 

## Slide 18: Expected Challenges
Delay in SRS and design finalisation & approval by department. This is mainly because of difference in opinion between key decision makers and slow approval process within the department.
Rework on approved design & SRS at the time of UAT or just before going live. This happens when approvals are provided by department’s nodal officer in order to expedite the Web portal development without involving or getting approval of senior authorities during design finalisation.
On time review and approvals of various deliverables by department.
Availability of Database Schema at time of Development of Backend Structures and Tables

## Slide 19
Methodology We Used
Will co-ordinate and provide timely update at every stage till launch

## Slide 20: Management Team Details – NetCreativeMind
Mr. Manoj Kumar Garg [CEO]
  Mobile Number : +91-9810978433
  Email : manoj@netcreativemind.com
Mr. Nikhil Kumar Singh [PM]
  Mobile Number : +91-9810306268
  Email : nikhil.singh@netcreativemind.com
Mr. Rohit Tiwari[Sales Manager]
  Mobile Number : +91-9911729706
  Email : rohit.tiwari@netcreativemind.com
Mr. Mohammad Sajid [Technical Manager]
  Mobile Number : +91-9654936266
  Email : mohammad.sajid@netcreativemind.com

## Slide 21
Thank You